## Slide 1
Planning, logistics and organization in Chemical Industry.
Mathematical programming approaches to the planning and scheduling in chemical processes
Master in Chemical Engineering
University of Alicante.
José A. Caballero
Design and Scheduling Models.

## Slide 2
Planning and Scheduling
There is no a clear distinction between planning and scheduling models.
Planning try to answer the following questions:
  Which are the products to be manufactured?
  How much must be produced of each product?
  How must the products be manufactured?
  Which resources are required?
Scheduling problems answer the following questions:
  Which are the units required for each product?
  In which order must be produced?
  When must be started each stage?

## Slide 3
Design of Batch Plants
Structural level
Assignment of tasks to equipment
Number of parallel units and/or intermediate storage
Sizing level
Equipment sizing
Scheduling level
Nature of production campaigns
  Length of campaigns
  Sequencing of products
Transfer policies
?
?
?

## Slide 4
Design of Batch Plants
Some considerations:
Not all the models deal with all levels:
  There are models that include the three levels
  Models for design and scheduling
  Models just for scheduling
The level of detail of each model is ‘case dependent’.
There are different formulations for the same problem with different numerical properties.
Even though there are some ‘generalist’ models (try to include all the alternatives) a specific model usually has better numerical performance.

## Slide 5
Road-Map for Batch Scheduling
(1) TASK TOPOLOGY:
- Single Stage (single unit or parallel units)
- Multiple Stage (multiproduct or multipurpose)
- Network
(2) EQUIPMENT ASSIGNMENT
- Fixed
- Variable
(3) EQUIPMENT CONNECTIVITY
- Partial
- Full
(4) INVENTORY STORAGE POLICIES
- Unlimited intermediate storage (UIS)
- Non-intermediate storage (NIS)
- Finite intermediate storage (FIS): Dedicated or shared storage units
- Zero wait (ZW)
(5) MATERIAL TRANSFER
- Instantaneous (neglected)
-Time consuming (no-resource, pipes, vessels)

## Slide 6
(6) BATCH SIZE:
- Fixed
- Variable (mixing and splitting operations)
(7) BATCH PROCESSING TIME
- Fixed
- Variable (unit / batch size dependent)
(8) DEMAND PATTERNS
- Due dates (single or multiple product demands)
- Scheduling horizon (fixed, minimum/maximum requirements)
(9) CHANGEOVERS
- None
- Unit dependent
- Sequence dependent (product or product/unit dependent)
(10) RESOURCE CONSTRAINTS
- None (only equipment)
- Discrete (manpower)
- Continuous (utilities)
i
i’
changeover
i’
Road-Map for Batch Scheduling

## Slide 7
(11) TIME CONSTRAINTS
- None
- Non-working periods
- Maintenance
- Shifts
(12) COSTS
- Equipment
- Utilities (fixed or time dependent)
- Inventory
- Changeovers
(13) Degree of certainty
- Deterministic
- Stochastic
Road-Map for Batch Scheduling

## Slide 8
Road-Map for Optimization Approaches
(A) TIME DOMAIN REPRESENTATION
- Discrete time
- Continuous time
(B) EVENT REPRESENTATION
DISCRETE TIME
- Global time intervals
CONTINUOUS TIME
- Time slots
- Unit-specific direct precedence
- Global direct precedence
- Global general precedence
- Global time points
- Unit- specific time event
(C) MATERIAL BALANCES
- Lots (Order or batch oriented)
- Network flow equations (STN or RTN problem representation)
(D) OBJECTIVE FUNCTION
- Makespan
- Earliness/ Tardiness
- Profit
- Inventory
- Cost
7
6
5
4
3
2
1
9
8
19
18
11
10
22
21
20
25
24
23

## Slide 9
OPTIMAL DESIGN AND SCHEDULING OF MULTIPRODUCT PLANTS

## Slide 10
Flowshop Plants. Single Product Campaigns (ZW).
(Kocis & Grossmann, 1988)
Problem Statement:
Consider a flowshop plant with fixed product demands. The objective consists of selecting the sizes and number of parallel units operating out of phase that minimize the investment costs.
Data:
  N: Number of products to be produced.
  M: Number of stages in the batch plant.
  τi,j: Processing time of product i in stage j (h).
  Sij: Size factor for product i in stage j (l/kg).
  H: Horizon time (h).
  Qi: Demand of product I (kg).
  αj, βj: Cost coefficient and cost exponent for unit j.
  VjL, VjU: Lower and upper bounds of volumes.

## Slide 11
I. Flowshop Plants. Single Product Campaigns (ZW).
Variables:
  Vj: Volume of unit in stage j.
  Bi: Size of the batch of product i.
  ni: Number of batches of product i.
  NPj: Number of units in parallel in stage j.
  TLi: Cycle time of product i.
  θi: Time allocated product i from time horizon H

## Slide 12
I. Flowshop Plants. Single Product Campaigns (ZW).
Horizon constraints:
A single product campaign with no intermediate storage (ZW) available facilitates the timing considerations at the design stage. Consider first the case of one unit per stage:
The cycle time can be determined from the following equation:
(1)
Since the number of batches (ni) is normally large, the heads and tails in the schedule can be neglected. The production time θi devoted to each product can be approximated by:
(2)
(3)

## Slide 13
I. Flowshop Plants. Single Product Campaigns (ZW).
Horizon constraints (cont.):
Substituting eq. 3 in eq. 2, the horizon constraint for one unit per stage can be written in terms of the number of batches ni:
(4)
For the case when NPj parallel units might be used at each stage, the cycle time is expressed as follows:
(5)
The horizon constraints for flowshop plants with parallel units is then:
(6)
(7)

## Slide 14
I. Flowshop Plants. Single Product Campaigns (ZW).
The volume Vj has to be able to process all the products i:
(8)
The right hand side represents the actual volume needed by each product.
The number of batches ni for each product I is given by:
(9)
Finally the investment cost is:
(9)

## Slide 15
I. Flowshop Plants. Single Product Campaigns (ZW).
Model MINLP (I).
Where, for a maximum of K parallel units, the bounds can be calculated as follows:
Non-Linear no-convex
Non-Linear

## Slide 16
I. Flowshop Plants. Single Product Campaigns (ZW).
Model MINLP (II): Convexification
Previous model can be covexified by using a exponential transformation. Besides, the resulting NLP will be in terms of binary variables instead of integer (NPj) variables.
Where the new variables are:
If we substitute in the objective function we get:
That is a convex function

## Slide 17
I. Flowshop Plants. Single Product Campaigns (ZW).
Model MINLP (II): Convexification
Substituting in (8) and taking logarithms:
Linear
Similarly for the time cycle constraints:
Linear
The time horizon constraint yields:
Convex
npj can be expressed in terms of binary variables as follows:

## Slide 18
I. Flowshop Plants. Single Product Campaigns (ZW).
Model MINLP (II):
Convex Model

## Slide 19
I. Flowshop Plants. Single Product Campaigns (ZW).
Discrete Sizes (Voudouris & Grossmann, 1992)
In practice, it is often the case that only standard sizes for the vessels are available.
A straightforward, and rigorous approach consists of defining the following binary variable:
An adding the following constraints to the previous model:
Assume that the equipment size in stage j is given by the set:

## Slide 20
I. Flowshop Plants. Single Product Campaigns (ZW).
Discrete Sizes (MILP):
A better approach consists of taking advantage of the discrete sizes and reformulate the problem as a MILP. Considering one unit per stage:
From eq. 2 and eq. 9:
Let the inverse of the volume expressed as a linear combination of the inverse of discrete sizes:
Substituting:

## Slide 21
I. Flowshop Plants. Single Product Campaigns (ZW).
Discrete Sizes (MILP) (one unit per stage):

## Slide 22
I. Flowshop Plants. Single Product Campaigns (ZW).
Discrete Sizes (MILP) (Multiple units per stage):
If we consider units in parallel, we can define:
The new values for cycle time can be calculated a priori:
And therefore:

## Slide 23
II. Flowshop Plants. Mixed Product Campaigns. UIS
(Birewar & Grossmann, 1989)
Mixed product campaigns involve sequencing of individual batches of the different products.
Assumptions:
  One unit per stage
  Unlimited Intermediate Storage (UIS)
  The costs of storage tanks is neglected.
  Cleanup times can be neglected
Data:
  N: Number of products to be produced.
  M: Number of stages in the batch plant.
  τi,j: Processing time of product i in stage j (h).
  Sij: Size factor for product i in stage j (l/kg).
  H: Horizon time (h).
  Qi: Demand of product I (kg).
  αj, βj: Cost coefficient and cost exponent for unit j.
  VjL, VjU: Lower and upper bounds of volumes.

## Slide 24
The cycle time for a plant with one unit per stage operating with UIS police is:
(1)
Variables:
  Vj: Volume of unit in stage j.
  Bi: Size of the batch of product i.
  ni: Number of batches of product i.
II. Flowshop Plants. Mixed Product Campaigns. UIS
The horizon constraint is then simply given by:
(2)

## Slide 25
The model can be written as the following NLP:
Objective function
Capacity constraint
Horizon constraint.
Remember ni = Qi/Bi
Bounds
The max constraints have been removed and written in terms of a set of inequalities
II. Flowshop Plants. Mixed Product Campaigns. UIS

## Slide 26
Remarks:
The NLP is non-convex, but it can be convexified as in the previous model
EXERCISE: Develop the convexified version of the model
If discrete sizes are involved, the problem can be reformulated as a MILP.
EXERCISE: Develop the MILP model for discrete sizes.
For flowshops with one unit per stage the above NLP will provide a lower bound of the equipment cost to plants that implement transfer policies other than UIS (e.g. zero-wait)
II. Flowshop Plants. Mixed Product Campaigns. UIS

## Slide 27
UIS models are relatively simple because we have a nice closed form expression for the cycle time.
In ZW or if the cleanup times are significant, this task is more complex:
  Determining the cycle does require determining a given sequence of production that we have avoided in previous cases.
The objective of this section is to show that for a fixed number of batches ni, i = 1… N, calculating the cycle time can be reduced to a LP model.
III. Flowshop Plants. Mixed Product Campaigns. ZW

## Slide 28
Calculation of slack times (Birewar & Grossmann, 1989)
In cyclic scheduling with ZW policy forced idle times arise at different stages.
These idle times are sequence dependent.
Fortunately, these idle times can be computed a priori.
Consider the following example (two products, three production stages):
5
2
3
1
5
3
III. Flowshop Plants. Mixed Product Campaigns. ZW

## Slide 29
Calculation of slack times
5
2
3
1
5
3
SLAB1 = 1
SLAB2 = 0
SLAB3 = 2
Without cleanup times
With cleanup times
5
2
3
1
5
3
SLAB1 = 0
SLAB2 = 0
SLAB3 = 1
III. Flowshop Plants. Mixed Product Campaigns. ZW

## Slide 30
Calculation of slack times: Algorithm
Product i followed by product k with cleanup times CLi,k,j
Define start times for product k assuming the bottleneck occurs in stage 1:
  Calculate slacks dj corresponding to assumption in step 1, and the smallest corresponding value δ
Calculate the actual slacks SLi,k,j
III. Flowshop Plants. Mixed Product Campaigns. ZW

## Slide 31
Graphical ‘explanation’ of the algebraic approach
5
2
3
1
5
3
Without cleanup times
Step 1: Assume that the bottleneck is in stage 1

## Slide 32
Graphical ‘explanation’ of the algebraic approach
Without cleanup times
Step 2: Calculation of ‘overlapping’
5
2
3
1
5
3
Minimum time at which product B could start in stage j (sequence A-B)

## Slide 33
Graphical ‘explanation’ of the algebraic approach
5
2
3
1
5
3
Without cleanup times
Step 2: Calculation of ‘overlapping’

## Slide 34
Graphical ‘explanation’ of the algebraic approach
5
2
3
1
5
3
Without cleanup times
Step 3: Correction of the overlapping and calculation of slacks

## Slide 35
Without cleanup times
Calculation of slack times: Previous Example
III. Flowshop Plants. Mixed Product Campaigns. ZW

## Slide 36
With cleanup times
5
2
3
1
5
3
Step 1: Assume that the bottleneck is in stage 1
Graphical ‘explanation’ of the algebraic approach

## Slide 37
5
2
3
1
5
3
With cleanup times
Graphical ‘explanation’ of the algebraic approach
Step 2: Calculation of ‘overlapping’
Minimum time at which product B could start in stage j (sequence A-B)

## Slide 38
5
2
3
1
5
3
With cleanup times
Graphical ‘explanation’ of the algebraic approach
Step 2: Calculation of ‘overlapping’

## Slide 39
5
2
3
1
5
3
With cleanup times
Graphical ‘explanation’ of the algebraic approach
Step 3: Correction of the overlapping and calculation of slacks

## Slide 40
With cleanup times
Note:
Calculation of slack times: Previous Example
III. Flowshop Plants. Mixed Product Campaigns. ZW

## Slide 41
Calculation of cycle time.
Determining the optimal cycle sequence of NB individual batches can be viewed as a traveling salesman problem (TSP):
Nodes correspond to individual batches 1, 2, … 5,
The two-way edges between every par l and m represent potential transitions l to m or m to l.
1
2
3
4
5
III. Flowshop Plants. Mixed Product Campaigns. ZW

## Slide 42
Calculation of cycle time.
Note that each pair of batches l, m can correspond to the same product or to different products
For the cycle time (CT), we only need to analyze one stage, say stage 1.
III. Flowshop Plants. Mixed Product Campaigns. ZW

## Slide 43
Calculation of cycle time.
Only one out
Only one in
Subtours may occur
1
2
3
4
Let B set batches, Q subsets of batches
Above Q = {1,2}, Q = {3,4}
III. Flowshop Plants. Mixed Product Campaigns. ZW

## Slide 44
Calculation of cycle time (ATSP)
III. Flowshop Plants. Mixed Product Campaigns. ZW

## Slide 45
Aggregation model
III. Flowshop Plants. Mixed Product Campaigns. ZW
From a design point of view a major difficulty is that we need to know the number of batches NB in advance, as well as their product identity.
In design problems we need (want) to determine the number of batches ni for each product i.
To obtain a model that explicitly incorporates the calculation of the number of batches, we will consider an aggregation of the previous problem in terms of NP products.
We define NPRi,k= number of changeovers from product i to product k

## Slide 46
We define NPRi,k= number of changeovers from product i to product k
Let B(i) = {m | batch m correspond to product i}
Node l produces i node m produces k
The number of batches, can then be calculates as:
Aggregation model
III. Flowshop Plants. Mixed Product Campaigns. ZW

## Slide 47
Can be solved as LP treating NPRik  0 (as continuous)
Aggregation model
III. Flowshop Plants. Mixed Product Campaigns. ZW

## Slide 48
If in the previous model single product campaigns (SPC) can be obtained by simple specifying the last inequality as an equality.
Remarks:
If subcycles are obtained using the LP model we can use subtour elimination constraints.
Aggregation model
In the graph representation of this model, the nodes correspond to products and the arcs to number of changeovers.
A
B
C
NPRi,k
III. Flowshop Plants. Mixed Product Campaigns. ZW

## Slide 49
Aggregation model: Example
4 products, 20 batches
nA = 7
nB = 5
nC = 3
nD = 5
Solution from LP
A
B
C
D
3
3
3
2
5
4
III. Flowshop Plants. Mixed Product Campaigns. ZW

## Slide 50
Aggregation model: Example loop breaking procedure
A
B
C
D
3
3
3
2
5
4
B
D
2
2
+
3
A
B
C
D
3
3
3
4
B
B
B
D
D
A
4
3
A
B
C
D
3
3
3
+
B
B
B
D
D
A
A
A
A
A
III. Flowshop Plants. Mixed Product Campaigns. ZW
B
B
B
D
D
A
A
A
A
A
C
D
B
A
C
D
C
A
B
D

## Slide 51
Design model:
III. Flowshop Plants. Mixed Product Campaigns. ZW
The problem of determining continuous sizes can simply be formulated by treating the number of batches ni as variable and by setting a constraint for the cycle time (CT). The model can be written as follows:

## Slide 52
Remarks:
If discrete sizes are involved, the problem can be reformulated as a MILP.
EXERCISE: Develop the MILP model for discrete sizes.
III. Flowshop Plants. Mixed Product Campaigns. ZW
The previous NLP has a unique solution.
Its remarkable feature is that it is a model that accurately anticipate the effect of scheduling at design stage.